## Slide 1: John Day River Steelhead Overshoot Logan Breshears
Picture: Jonny Armstrong

## Slide 2
Raw/meta PIT Data
Raw/meta PIT Data (backup)
Data trimming/filtering
Sort into sub-basins
Set data time constraints (years)
Sort by salmonid species
Run survival analysis
Visualize
Run comparative analysis
Visualize
Raw/meta Acoustic Data
Automate process
Raw/meta Acoustic Data (backup)
Replicate PIT analysis with acoustic data
Online github repository
Review steps
Publish
Reproducibility check
Reproducibility check
Reproducibility check
Goal!!

## Slide 3: Quarter Goals
Run survival and comparative analyses for Adult steelhead migration (2005-2020).
    I’ve begun writing code for the survival analyses.
    Comparative analysis should just be a repeat of survival.
Familiarize myself with GitHub, and Sourcetree
Typesetting with Latex and Markdown
Clean my code structure
Not reverting back to old habits
    Excel

## Slide 4: Successes
Setting up an FTP server for accessing data
Coding structure is clean, legible, and repeatable
File structure has improved significantly
Feel comfortable using GitHub and Sourcetree
Use Markdown and Latex more frequently
Not reverting back to old habits as often

## Slide 5: Setbacks
Downloading and trimming metadata from online database
  Initial data downloads were incomplete
  Set up an FTP server for ease of data transfer and integration with R
Wrapping up research and ODFW commitments
  End of year reporting (multiple permits)
  Project updates/presentations for grant funders
  Coordinating data retrieval
  Thinking ahead to ‘21 & ’22 for future acoustic research
Time allocation

## Slide 6: Future Goals
Finish up PIT tag analyses by the end of Dec.
Retrieve and download acoustic data from sites downstream of John Day Dam (Dec – Jan)
    Upstream locations spring term
Sort acoustic data and format similar to PIT detections
    Using downstream locations as reproducibility check
Run analyses for acoustic detections
Run similar analyses for downstream cold water tributary use